| Title: | # TERRA – Tracking and Environmental Real-time Response Apparatus |
| --- | --- |
| Program Summary (100 words max): | The TERRA project (Tracking and Environmental Real-time Response Apparatus) is an automated flood and environmental monitoring system designed to improve flood management in Bangladesh. Each autonomous unit gathers real-time data on water levels (HC-SR04), temperature and humidity (DHT22), and air quality (MQ135). Powered by solar, battery, and AC/DC backups, TERRA ensures uninterrupted operation during floods. It supports Wi-Fi, GSM, and LoRaWAN connectivity for reliable data transmission. By installing TERRA units in flood-prone regions, the project enhances proactive flood risk management. Future expansion with additional sensors and predictive models will aid agricultural planning, infrastructure development, and national food security, fostering resilient communities. |
| Project Amount: | 500000 |
| Contact Person: | Samsun Naher |
| Date of submission: | 15 January, 2025 |

- Background and Rationale (Max. 100 words)

Please mention why this project is important

Bangladesh's unique hydrogeology makes it highly vulnerable to floods, cyclones, and climate change impacts. From 1900-2016, 90 major floods caused 52,437 deaths, affecting 32 million people (Islam et al.,2022). Recent floods have isolated over 1 million in Noakhali, Cumilla, Feni, Chattogram, and Moulvibazar. Erratic rainfall, inadequate preparedness, and poor infrastructure exacerbate flood impacts. While urban areas benefit from flood forecasting (FFWC), remote regions lack real-time monitoring due to insufficient technology and resources. The government allocated USD 2.5 million to early warning systems(Perera et al.,2019), yet cost-effective, real-time flood monitoring devices remain scarce, hindering timely alerts and effective flood management in vulnerable communities.

- Project Objective (Max. 100 words)

Please mention the objectives of the project and its alignment with the long-term vision

Project TERRA envisions starting from Maijdee,Noakhali deploying 10 mvp (minimum viable product) micro climate sensor and then eventually transforming Bangladesh into a climate-resilient nation through real-time environmental monitoring and data-driven solutions. In the short term, it aims to enhance flood preparedness, ensure precise resource allocation, and foster community resilience through literacy programs. Long-term goals include establishing a micro-climate analysis framework across Bangladesh including supporting sustainable agriculture, resilient infrastructure planning, proactive policy development, and minimizing climate-induced losses. By integrating grassroots engagement and advanced analytics, TERRA seeks to build a future-ready nation capable of adapting to climate challenges,ensuring economic and social stability.

- Project Beneficiaries

Please mention the immediate/primary/direct beneficiaries and secondary/indirect beneficiaries

Immediate beneficiaries - Flood Preparedness and Real-Time Decision Support TERRA’s real-time monitoring provides critical flood data to authorities, enabling swift responses and early warnings for communities. This preparedness minimizes risks to lives and property, ensuring communities are better equipped to handle flood emergencies. - Resource Allocation TERRA’s centralized dashboard enables precise targeting of resources to affected zones, ensuring prioritized support for vulnerable communities. This efficient allocation maximizes the impact of relief efforts, bringing timely aid to those in need. - Community Awareness and Resilience Flood campaigns and literacy programmes inform communities of local flood risks, fostering a culture of preparedness. This encourages preemptive safety measures, reduces panic, and enhances community resilience during flood events. Secondary beneficiaries - Adaptation to Climate Change and Infrastructure Resilience Authorities may monitor climate change through ongoing data gathering, which informs resilient infrastructure and urban development. Bangladesh's ability to create climate-adaptive communities ready for future catastrophes is strengthened by data-driven advancements.. - Economic and Social Stability TERRA strengthens economic resilience in vulnerable areas by minimizing flood-induced losses, which lowers recovery costs and promotes regional development. This stability protects investments and improves the standard of living for locals. - Sustainable Agriculture Production TERRA’s data on soil moisture and other conditions supports sustainable agriculture, crucial for food security. These insights will help rural communities reliant on farming to adapt to changing environmental conditions. - Support for Proactive Policy Development Ongoing environmental monitoring strengthens national climate resilience by supporting sustainable urban development, water resource management, and agriculture while enabling policymakers in adapting to climate hazards. - Long-Term Risk Management TERRA’s predictive capabilities help identify high-risk zones by flood zone mapping and track flood trends, supporting resilient infrastructure planning. Data-driven mitigation measures, such as flood barriers and buffer zones, reduce disaster risks and enhance community resilience across Bangladesh

- Project Activities

Please mention the detailed planned activities of the projects. Activities should be clearly defined, and the information presented should be well-developed.

- Prototype Development: Manufacture and test 10 devices with environmental sensors. - Dashboard Development: Create a secure, user-friendly platform to visualize data. - Capacity-Building Workshops: Train stakeholders in device usage and data interpretation. - Climate Awareness Programs: Educate communities about environmental sustainability. - Data Deployment: Integrate devices and dashboard into a functional system.

Outreach Strategy:

| Objective | Media Channels | Details |
| --- | --- | --- |
| Enhance community engagement | OOH- Out of home activity : Community meetings and workshops in flood-prone areas to introduce the TERRA system and its benefits. | Conduct monthly offline workshops and quarterly social media campaigns to ensure sustained engagement. |
| Raise awareness and collaborate about flood preparedness | OOH- Out of home activity : Educational campaigns in schools and local community centers to improve awareness about flood risks and preparedness measures. | Publish user-friendly guides and infographics on how to interpret TERRA data for flood preparedness Collaboration with local NGOs to organize training sessions on using TERRA data for early warning and decision-making. |
| Provide climate insight and disaster management in due time | OOH- Out of home activity Online Platform based activity | Providing data visualization and disaster coordination using autonomous,satellite and participatory data management in the platform |
| Making the initiative familiar among piloting area | Social media platforms (e.g., Facebook, Twitter, Instagram) to disseminate updates, success stories, and real-time flood data insights. | Share impact stories and testimonials from communities benefiting from TERRA to encourage widespread adoption. |

- Project Timeline and Schedule:

Please share a detailed timeline through a Gantt chart.

Download the Gantt chart here: https://emkcenter.org/wp-content/uploads/2023/12/EMK-Small-Grant-2024-GANTT-CHART-TEMPLATE.xlsx

Attached in the Gantt chart

- Project Outcome:

Please mention the outcome expected upon the completion of the project. Outcomes should indicate what change or result is anticipated if project objectives are achieved.

- 10 functioning prototypes deployed in target locations. - Operational online data dashboard for environmental insights. - Stakeholders trained to use the devices and data. - Enhanced community awareness of climate change and disaster preparedness.

- Project Monitoring and Evaluation

Please share the Monitoring and Evaluation Plan using the given Log frame

| Objective | Activities | Outcome | Outcome Indicator | Means of verification | Risk Mitigation |
| --- | --- | --- | --- | --- | --- |
| Develop 10 Prototypes for Environmental Monitoring | Procure materials and components for prototype development. Design and assemble 10 monitoring device prototypes. Conduct functionality tests and refine devices based on feedback. | Successful development of 10 functional prototypes ready for field deployment. | Number of prototypes developed and successfully tested. | Prototype design documentation, testing reports, and photos/videos of assembled devices. | Regular supplier follow-ups for timely delivery of materials. Allocate buffer time for design modifications. |
| Build a User-Friendly Online Dashboard for Data-driven decision-making | Design and develop a real-time data dashboard. Integrate device data into the dashboard system. Perform system testing and user feedback analysis. | Enhanced decision-making for flood risk management and resource allocation | Usage statistics of dashboards | Dashboard usage analytics, feedback from local authorities | Use agile development for iterative feedback incorporation. Employ backup storage solutions to prevent data loss. . |
| Community resilience and awareness | Conduct workshops and literacy campaigns | Improved community preparedness and awareness of flood risks | Number of participants and surveys showing increased awareness levels | Attendance logs, pre- and post-campaign surveys | Engage local NGOs to maximize outreach and use culturally relevant content in campaigns. |
| Sustainable infrastructure planning | Analytical insights shared with policymakers | Inclusion of data-driven strategies in urban planning and policy development | Policies and planning documents referencing TERRA data | Meeting minutes, published policy drafts | Collaborate with policymakers early to align objectives and include technical experts in consultations |
| Long-term climate adaptation strategies | Flood zone mapping and trend analysis | Improved long-term planning and resource optimization | Reports and maps indicating high-risk zones | Published flood zone maps, risk mitigation plans | Ensure data quality through periodic validation, and integrate predictive modeling to refine future projections. |

- Key personnel (please provide a short bio of the key personnel including roles and expertise within 100 words. Details CV can be attached as annexes)

Provide details of the core team members of the project

Samsun Naher, Project Lead, is pursuing an MSc in Oceanography with expertise in ocean acidification and environmental monitoring. An early-career researcher, she has published research work and is skilled in programming (R, Python), GIS, and remote sensing, with a strong foundation in field observations and analytical writing. Mahadi Sajjad Neloy, Embedded Systems Engineer, specializes in IoT and embedded systems, with expertise in C++, Python, and Linux. He has led advanced projects in real-time monitoring solutions. Md. Iftekharul Islam, Public Relations Coordinator, has over five years of experience in operations and public relations, excelling in stakeholder engagement, strategic planning, and outreach.

- Professional references:

Please include references’ name, organization, email, and phone number. References should be able to validate the applicant’s ability to work effectively, achieve results, and successfully implement similar activities within the past three (3) years.

| Reference 01 |  | Reference 02 |  |
| --- | --- | --- | --- |
| Name | Ashfaqur Rahman Chowdhury | Name | Suraiya Akther |
| Designation | General Secretary | Designation | Executive Director |
| Organization | Youth Notion | Organization | Dishari |
| Email ID | ashfaq@youthnotion.org | Email ID | dishari.2023@gmail.com |
| Phone Number | +8801787600900 | Phone Number | +8801864272727 |

- (Optional) Please use the space below to list additional citations in support of this project.

M.A. Islam, M.A. Chisty, A. Fuad, M.M. Rahman, M. Muhtasim, S.E.A. Dola, F.J. Biva, N.A. Khan, Using ARC-D toolkit for measuring community resilience to disasters, Sustainability 14 (3) (2022), https://doi.org/10.3390/su14031758. Perera, D., Seidou, O., Agnihotri, J., Rasmy, M., Smakhtin, V., Coulibaly, P., & Mehmood, H. (2019). Flood early warning systems: A review of benefits, challenges and prospects. UNU-INWEH, Hamilton.

- Clarifications

- I understand that EMK may share this application, internally as part of the due diligence process or if EMK identifies opportunities to strengthen or fund an application by connecting with other entities for appropriate consideration.

- By submitting this application, I certify that the answers to the questions are accurate to the full extent of my knowledge.

Full name of the Applicant:	Samsun Naher	                                  Date:15 January, 2025